## Detail_plan (2)
No | Task | Status | ICE TECH | PROGRAMMER | ERP |  | .NET
[5 empty] | ERP START | ERP END | NEW START DATE | NEW END DATE | NEW Start DATE FROM DEV | NEW TARGET DATE FROM DEV | Remark | Est Coding Manday | Est Coding Manday
1 | Build Fspec
| GL002: BILL PAYMENT | PROCESS | KTP |  | 2017-11-02 | 2017-11-02
| PO006_1 : PO FORM | OPEN | KTS |  | 2017-11-03 | 2017-11-06
| GL004 : MMX DSA ,DSH (SALE DETAIL)(FILE ARTS) | OPEN | KTS |  | 2017-11-07 | 2017-11-08
| BOM001 : SPA REPORT | OPEN | KTS |  | 2017-11-09 | 2017-11-10
2 | Send Fspec
Submit Spec To RD
RD Review Fspec
RD Confirm Fspec
Reserve Edit Fspec
3 | Build
| PO001 : LINFOX PR INTERFACE | PROCESS | AMO | POP |  |  | 2017-10-30 | 2017-11-07 | 2017-11-07 | 2017-11-07 | Wait for Integrate Web Service | 7 | 7
| PO005 : MMX PR/PO DIRECT | PROCESS | AMO | POP |  |  | 2017-11-08 | 2017-11-09 | 2017-11-13 | 2017-11-13 | Wait for Integrate Web Service | 2 | 2
| PO002 : MMX OUTBOUND PO TO PO | OPEN | AMO | POP | 2017-11-06 | 2017-11-07 | 2017-11-10 | 2017-11-17 | 2017-11-18 | 2017-11-22 | Wait for Integrate Web Service | 2 | 2
| PO008 : CEDAR TEXT FILE TO PO | PROCESS | AMO | POP |  |  | 2017-11-14 | 2017-11-15 | 2017-11-18 | 2017-11-20 | Wait for Integrate Web Service | 2 | 2
| PO003 : LINFOX GR TO RCP-AP | PROCESS | AMO | POP |  |  | 2017-11-16 | 2017-11-13 | 2017-11-24 | 2017-11-24 | Wait for Integrate Web Service | 3 | 3
| PO004 : DRT TO GOOD RECEPT | PROCESS | AMO | POP |  |  | 2017-11-20 | 2017-11-13 | 2017-11-13 | 2017-11-20 | Wait for Integrate Web Service | 2 | 2
| PO007 : Text File PO (ERP) to U-info | OPEN | AMO | POP |  |  | 2017-11-22 | 2017-11-23 | 2017-11-24 | 2017-11-24 | Wait for Integrate Web Service | 2 | 2
| PO006_2 :PO_TEXT_FILE | OPEN | AMO | POP |  |  | 2017-11-24 | 2017-11-20 | 2017-11-30 | 2017-11-30 | Wait for Integrate Web Service | 2 | 2
| PO006_1 : PO FORM | OPEN | KTS | KTS | 2017-11-13 | 2017-11-15 | 2017-11-10 | 2017-11-14 |  |  |  | 3 | 3
| GL001 : MMX DFT(GL001) | OPEN | KTP | Champ |  |  | 2017-11-07 | 2017-11-10 | 2017-11-08 | 2017-11-15 | สูตรใน Field ไม่ได้ เป็น fix code | 4 | 4
| INV005_2 : DUS,WUS | OPEN | KTP | POP |  |  | 2017-11-13 | 2017-11-14 | 2017-12-10 | 2017-12-10 | Wait for Integrate Web Service | 2 | 2
| GL002 : BILL PAYMENT | OPEN | KTP | Champ |  |  | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-17 | Wait for Integrate Web Service | 2 | 2
| GL004 : MMX DSA ,DSH (SALE DETAIL)(FILE ARTS) | OPEN | KTP | Champ |  |  | 2017-11-16 | 2017-11-20 | 2017-11-17 | 2017-11-19 | Wait for Integrate Web Service | 3 | 3
| AP004 : Interface Text File U-info from bill placement to AP Invoice | OPEN | KWL | Champ |  |  | 2017-11-08 | 2017-11-09 | 2017-11-25 | 2017-12-27 | Wait for Integrate Web Service | 2 | 2
| AP001 : Interface EDI File from Supplier to AP Invoice | OPEN | KWL | Champ | 2017-11-07 | 2017-11-10 | 2017-11-10 | 2017-11-14 | 2017-11-19 | 2017-11-23 | Wait for Integrate Web Service | 3 | 3
| AP002 : Report Text file Payment(ERP) to Citibank | OPEN | KWL | Champ |  |  | 2017-11-17 | 2017-11-17 | 2017-11-23 | 2017-11-25 | Wait for Integrate Web Service | 3 | 3
| INV001 : LINFOX GI TO INV | OPEN | KTS | POP |  |  | 2017-11-10 | 2017-11-23 | 2017-12-10 | 2017-12-10 | Wait for Integrate Web Service | 2 | 2
| INV005_1 : MMX INV MOVEMENT (DIN,PIN,WIN) | OPEN | KTS | POP |  |  | 2017-11-14 | 2017-11-25 | 2017-12-10 | 2017-12-10 | Wait for Integrate Web Service | 3 | 3
| BOM001 : SPA REPORT | OPEN |  | POP | 2017-11-18: 2017-12-10; 2017-11-22: 2017-12-10 | Wait for Integrate Web Service | 4 | 4
| PO006 :Report PO FORM(ERP) to Supplier by email | OPEN |  | POP | 2017-11-18: 2017-12-10; 2017-11-22: 2017-12-10 | Wait for Integrate Web Service | 4 | 4
| INV005_3 : MMX INV MOVEMENT (DEX) | OPEN | KTS | POP |  |  | 2017-11-17 | 2017-11-27 | 2017-12-10 | 2017-12-10 | Wait for Integrate Web Service | 4 | 4
4 | Internal Test (Final) |  | CONSULT
5 | Check Point
6 | End To End Review
7 | Move Tests To Prod