## Sheet1 (hidden)
No | Customization | Customization Name | TEST DATE |  | FIX BUG
|  |  | Start Date | End Date | Start Date | End Date
1 | PO001 | LINFOX PR INTERFACE | 2017-11-30 | 2017-12-01 |  |  | POP | AMO
2 | PO002 | MMX OUTBOUND PO TO PO | 2017-11-30 | 2017-12-01 |  |  | POP | AMO
3 | PO003 | LINFOX GR TO RCP-AP | 2017-11-30 | 2017-12-01 |  |  | POP | AMO
4 | GL001 | MMX DFT(GL001) | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | CHAMP | KTP
5 | GL002 | BILL PAYMENT | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | CHAMP | KTP
7 | INV002 | INV005_2 : DUS,WUS | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06
6 | GL004 | MMX DSA ,DSH (SALE DETAIL)(FILE ARTS) | 2017-12-07 | 2017-12-07 | 2017-12-07 | 2017-12-07 | CHAMP | KTS
8 | PO005 | MMX PR/PO DIRECT | 2017-12-08 | 2017-12-08 |  |  | POP
9 | PO006_2 | PO_TEXT_FILE | 2017-12-08 | 2017-12-08 |  |  | POP
10 | PO004 | DRT TO GOOD RECEIPT AND INVENTORY | 2017-12-08 | 2017-12-08 |  |  | POP
11 | INV001 | LINFOX GI TO INV | 2017-12-06 | 2017-12-06 |  |  | KTS | KTS
12 | INV005_1 | MMX INV MOVEMENT (DIN,PIN,WIN) | 2017-12-11 | 2017-12-11 |  |  | CHAMP
13 | INV005_3 | MMX INV MOVEMENT (DEX) | 2017-12-11 | 2017-12-11 |  |  | CHAMP
15 | PO007 | Text File PO (ERP) to U-info | 2017-12-11 | 2017-12-11 |  |  | POP
16 | AP004 | Interface Text File U-info from bill placement to AP Invoice | 2017-12-11 | 2017-12-11 |  |  | POP
17 | AP001 | Interface EDI File from Supplier to AP Invoice | 2017-12-12 | 2017-12-12 |  |  | POP
14 | PO008 | CEDAR TEXT FILE TO PO | 2017-12-13 | 2017-12-13 |  |  | POP
BOM001 : SPA REPORT
AP002 : Report Text file Payment(ERP) to Citibank

## TEST_PLAN
No | Customization | Customization Name | TEST DATE |  | FIX BUG |  | PIC | ICE TECH | ICE CONSULT
|  |  | Start Date | End Date | Start Date | End Date
1 | PO001 | LINFOX PR INTERFACE | 2017-11-30 | 2017-12-01 |  |  | POP | AMO | MOD
2 | PO002 | MMX OUTBOUND PO TO PO | 2017-11-30 | 2017-12-01 |  |  | POP | AMO | MOD
3 | PO003 | LINFOX GR TO RCP-AP | 2017-11-30 | 2017-12-01 |  |  | POP | AMO | MOD
4 | GL001 | MMX DFT(GL001) | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | CHAMP | KTP | MIM
5 | GL002 | BILL PAYMENT | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | CHAMP | KTP | MIM
7 | INV002 | INV005_2 : DUS,WUS | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | KTP | KTP | MIM
6 | GL004 | MMX DSA ,DSH (SALE DETAIL)(FILE ARTS) | 2017-12-07 | 2017-12-07 | 2017-12-07 | 2017-12-07 | CHAMP | KTS | AUM,OHM,MIM
8 | PO005 | MMX PR/PO DIRECT | 2017-12-04 | 2017-12-04 |  |  | POP | AMO | MOD
9 | PO006_2 | PO_TEXT_FILE | 2017-12-04 | 2017-12-04 |  |  | POP | AMO | MOD
10 | PO004 | DRT TO GOOD RECEIPT AND INVENTORY | 2017-12-04 | 2017-12-04 |  |  | POP | AMO | MOD
11 | INV001 | LINFOX GI TO INV | 2017-12-06 | 2017-12-06 |  |  | KTS | KTS | KTS
12 | INV005_1 | MMX INV MOVEMENT (DIN,PIN,WIN) | 2017-12-12 | 2017-12-12 |  |  | CHAMP | KTS | AUM,OHM
13 | INV005_3 | MMX INV MOVEMENT (DEX) | 2017-12-12 | 2017-12-12 |  |  | CHAMP | KTS | AUM,OHM
15 | PO007 | Text File PO (ERP) to U-info | 2017-12-06 | 2017-12-06 |  |  | POP | AMO | MOD
16 | AP004 | Interface Text File U-info from bill placement to AP Invoice | 2017-12-06 | 2017-12-06 |  |  | POP | AMO | TIFFY
17 | AP001 | Interface EDI File from Supplier to AP Invoice | 2017-12-07 | 2017-12-07 |  |  | POP | AMO | TIFFY
14 | PO008 | CEDAR TEXT FILE TO PO | 2017-12-07 | 2017-12-07 |  |  | POP | AMO | MOD
15 | BOM001 | SPA REPORT | ?? |  |  |  | KTS | KTS | AUM,OHM
16 | AP002 | Report Text file Payment(ERP) to Citibank | ?? |  |  |  | KWL | KWL | TIFFY
17 | INV001 | LINFOX GI TO INV | 2017-12-13 | 2017-12-13 |  |  | KTS | KTS | KTS